## Overview
Task Planner Overview
A clear summary of workload, progress, deadlines, and exported report contents.
Employee | Revision Ten Manager |  | Employee ID | R10-001 |  | Department | Academic Department |  | Generated | 2026-09-13
Total Tasks |  |  | Completed |  |  | In Progress |  |  | Overdue
17 |  |  | 2 |  |  | 6 |  |  | 10
Completion Rate |  |  | Estimated Hours |  |  | Actual Hours |  |  | Remaining Hours
11.76% |  |  | 129 |  |  | 50 |  |  | 79
CURRENT WORKWEEK · 13 Sep–17 Sep 2026
Task | Project | Priority | Status | Due | Progress
Complete curriculum outline, topic, competences, duration and draft pack | Academy Stage 2–8 Test Program | High | Not Started | 2026-09-13 | 80%
Review curriculum QA and lock release | Academy Stage 2–8 Test Program | High | Not Started | 2026-09-14 | 0%
On-hold coordination test | IT | Medium | On Hold | 2026-09-15 | 25%
Quarterly academic performance review | Academic | High | In Progress | 2026-09-15 | 60%
Quarterly reporting test | Strategic | High | Not Started | 2026-10-23 | 15%
STATUS SUMMARY |  |  |  | PROJECT WORKLOAD
Status | Tasks | Share |  | Project | Tasks | Completed | Est. Hrs | Actual Hrs
Not Started | 7 | 41.18% |  | Academic | 5 | 1 | 53 | 33
In Progress | 6 | 35.29% |  | Academy Late-Stage Lifecycle Test | 1 | 0 | 2 | 0
Completed | 2 | 11.76% |  | Academy Stage 2–8 Test Program | 2 | 0 | 4 | 0
On Hold | 2 | 11.76% |  | Administration | 1 | 1 | 2 | 2
Cancelled | 0 | 0% |  | IT | 2 | 0 | 12 | 2
Overdue | 10 | 58.82% |  | Marketing | 3 | 0 | 27 | 8
|  |  |  | Operations | 2 | 0 | 9 | 3
|  |  |  | Strategic | 1 | 0 | 20 | 2
HOW TO USE THIS EXPORT
1. Start with Overview for the main workload and performance summary.
2. Use Tasks for the complete editable task register, links, dates, progress, and hours.
3. Weekly, Monthly, and Quarterly Report sheets are formatted for management review and PDF printing.
4. Update only the task register when importing the workbook back into the application.
5. Common task fields include inline dropdowns; no Lists or hidden validation sheet is included.

## Employee Profile
Employee Profile
Local employee information used by exported reports.
Field | Value
Full Name | Revision Ten Manager
Employee ID | R10-001
Academy Email | revision10@andalusia.net
Department | Academic Department
Job Title | Academy Manager
Phone
Working Week | Sunday–Thursday
Last Saved | 2026-09-13T11:40:31

## Tasks
Task Register
Edit task details here or import this sheet back into the application.
Tip: use filters in the header row. Status, priority, deliverable type, and recurrence include dropdowns.
Task ID | Task Name | Project | Task Category | Deliverable Type | Priority | Status | Start Date | Due Date | Progress % | Estimated Hours | Actual Hours | Variance | Recurrence | Link | Notes
TSK-1789288625411 | Complete curriculum outline, topic, competences, duration and draft pack | Academy Stage 2–8 Test Program | Program Tracking & Monitoring |  | High | Not Started | 2026-09-13 | 2026-09-13 | 80% | 2 | 0 |  | None |  | Workflow assignment · Curriculum
TSK-1789288563312 | Review curriculum QA and lock release | Academy Stage 2–8 Test Program | Program Tracking & Monitoring |  | High | Not Started | 2026-09-13 | 2026-09-14 | 0% | 2 | 0 |  | None |  | Workflow assignment · Curriculum
TSK-0002 | Update student attendance report | Academic | Program Tracking & Monitoring | Report | Medium | Completed | 2026-08-02 | 2026-08-03 | 100% | 4 | 4 |  | Weekly |  | Validate late submissions.
TSK-0001 | Prepare weekly lesson plan | Academic | Curriculum Design | Course Outline | High | In Progress | 2026-08-02 | 2026-08-06 | 75% | 8 | 6 |  | Weekly |  | Coordinate subject plans.
TSK-0004 | Review IT support tickets | IT | Program Tracking & Monitoring | Report | High | Not Started | 2026-08-05 | 2026-08-06 | 20% | 6 | 1 |  | Daily |  | Prioritize classroom issues.
TSK-0005 | Facilities inspection | Operations | Review & Quality Check | Report | Medium | Not Started | 2026-08-06 | 2026-08-10 | 0% | 5 | 0 |  | Monthly |  | Inspect safety and maintenance.
TSK-0003 | Design social media campaign | Marketing | Slide & Material Production | Slide Deck | High | In Progress | 2026-08-04 | 2026-08-12 | 45% | 12 | 5 |  | Monthly |  | Back-to-school campaign.
TSK-0007 | Parent communication newsletter | Marketing | Meetings with Client / Partner | Proposal | Medium | On Hold | 2026-08-01 | 2026-08-20 | 30% | 10 | 3 |  | Monthly |  | Awaiting final announcements.
TSK-26090802 | Completed test task | Administration | Administration | Report | Low | Completed | 2026-09-06 | 2026-09-07 | 100% | 2 | 2 |  | None |  | Automatically generated test task.
TSK-26090804 | Overdue follow-up test | Operations | Meetings & Coordination | Report | High | In Progress | 2026-09-03 | 2026-09-07 | 65% | 4 | 3 |  | None |  | Automatically generated test task.
TSK-26090801 | Today priority review | Academic | Review & Quality Check | Report | High | In Progress | 2026-09-08 | 2026-09-08 | 40% | 3 | 1 |  | None |  | Automatically generated test task.
TSK-1788861727457 | Review readiness and record delivery decision | Academy Late-Stage Lifecycle Test | Program Tracking & Monitoring |  | High | Not Started | 2026-09-08 | 2026-09-08 | 0% | 2 | 0 |  | None |  | Workflow assignment · Readiness, Delivery & Assessment
TSK-26090803 | Tomorrow content task | Marketing | Content Development | Web Page | Medium | Not Started | 2026-09-08 | 2026-09-09 | 0% | 5 | 0 |  | None |  | Automatically generated test task.
TSK-26090805 | Weekly planning test | Academic | Program Tracking & Monitoring | Course Outline | Medium | In Progress | 2026-09-06 | 2026-09-10 | 55% | 8 | 4 |  | None |  | Automatically generated test task.
TSK-0006 | Quarterly academic performance review | Academic | Program Tracking & Monitoring | Report | High | In Progress | 2026-07-15 | 2026-09-15 | 60% | 30 | 18 |  | Quarterly |  | Review academic KPIs.
TSK-26090807 | On-hold coordination test | IT | Meetings with Client / Partner | Proposal | Medium | On Hold | 2026-09-08 | 2026-09-15 | 25% | 6 | 1 |  | None |  | Automatically generated test task.
TSK-26090806 | Quarterly reporting test | Strategic | Program Tracking & Monitoring | Report | High | Not Started | 2026-08-24 | 2026-10-23 | 15% | 20 | 2 |  | None |  | Automatically generated test task.

## Weekly Report
Weekly Task Report
13 Sep 2026 – 17 Sep 2026
Employee |  | Revision Ten Manager |  |  |  | Employee ID |  | R10-001 |  |  | Generated |  | 2026-09-13
Department |  | Academic Department |  |  |  | Job Title |  | Academy Manager |  |  | Report |  | Weekly
Total Tasks |  | Completed |  | In Progress |  | Overdue |  | Estimated Hours |  | Actual Hours |  | Completion Rate
5 |  | 0 |  | 1 |  | 0 |  | 60 |  | 21 |  | 0%
Task | Project | Task Category | Deliverable Type | Priority | Status | Start | Due | Progress | Estimated | Actual | Variance | Recurrence | Link | Notes
Complete curriculum outline, topic, competences, duration and draft pack | Academy Stage 2–8 Test Program | Program Tracking & Monitoring |  | High | Not Started | 2026-09-13 | 2026-09-13 | 80% | 2 | 0 |  | None |  | Workflow assignment · Curriculum
Review curriculum QA and lock release | Academy Stage 2–8 Test Program | Program Tracking & Monitoring |  | High | Not Started | 2026-09-13 | 2026-09-14 | 0% | 2 | 0 |  | None |  | Workflow assignment · Curriculum
Quarterly academic performance review | Academic | Program Tracking & Monitoring | Report | High | In Progress | 2026-07-15 | 2026-09-15 | 60% | 30 | 18 |  | Quarterly |  | Review academic KPIs.
On-hold coordination test | IT | Meetings with Client / Partner | Proposal | Medium | On Hold | 2026-09-08 | 2026-09-15 | 25% | 6 | 1 |  | None |  | Automatically generated test task.
Quarterly reporting test | Strategic | Program Tracking & Monitoring | Report | High | Not Started | 2026-08-24 | 2026-10-23 | 15% | 20 | 2 |  | None |  | Automatically generated test task.
Status | Count
Not Started | 3
In Progress | 1
Completed | 0
On Hold | 1
Cancelled | 0
Overdue | 0

## Monthly Report
Monthly Task Report
01 Sep 2026 – 30 Sep 2026
Employee |  | Revision Ten Manager |  |  |  | Employee ID |  | R10-001 |  |  | Generated |  | 2026-09-13
Department |  | Academic Department |  |  |  | Job Title |  | Academy Manager |  |  | Report |  | Monthly
Total Tasks |  | Completed |  | In Progress |  | Overdue |  | Estimated Hours |  | Actual Hours |  | Completion Rate
11 |  | 1 |  | 4 |  | 5 |  | 84 |  | 31 |  | 9.091%
Task | Project | Task Category | Deliverable Type | Priority | Status | Start | Due | Progress | Estimated | Actual | Variance | Recurrence | Link | Notes
Complete curriculum outline, topic, competences, duration and draft pack | Academy Stage 2–8 Test Program | Program Tracking & Monitoring |  | High | Not Started | 2026-09-13 | 2026-09-13 | 80% | 2 | 0 |  | None |  | Workflow assignment · Curriculum
Review curriculum QA and lock release | Academy Stage 2–8 Test Program | Program Tracking & Monitoring |  | High | Not Started | 2026-09-13 | 2026-09-14 | 0% | 2 | 0 |  | None |  | Workflow assignment · Curriculum
Completed test task | Administration | Administration | Report | Low | Completed | 2026-09-06 | 2026-09-07 | 100% | 2 | 2 |  | None |  | Automatically generated test task.
Overdue follow-up test | Operations | Meetings & Coordination | Report | High | In Progress | 2026-09-03 | 2026-09-07 | 65% | 4 | 3 |  | None |  | Automatically generated test task.
Today priority review | Academic | Review & Quality Check | Report | High | In Progress | 2026-09-08 | 2026-09-08 | 40% | 3 | 1 |  | None |  | Automatically generated test task.
Review readiness and record delivery decision | Academy Late-Stage Lifecycle Test | Program Tracking & Monitoring |  | High | Not Started | 2026-09-08 | 2026-09-08 | 0% | 2 | 0 |  | None |  | Workflow assignment · Readiness, Delivery & Assessment
Tomorrow content task | Marketing | Content Development | Web Page | Medium | Not Started | 2026-09-08 | 2026-09-09 | 0% | 5 | 0 |  | None |  | Automatically generated test task.
Weekly planning test | Academic | Program Tracking & Monitoring | Course Outline | Medium | In Progress | 2026-09-06 | 2026-09-10 | 55% | 8 | 4 |  | None |  | Automatically generated test task.
Quarterly academic performance review | Academic | Program Tracking & Monitoring | Report | High | In Progress | 2026-07-15 | 2026-09-15 | 60% | 30 | 18 |  | Quarterly |  | Review academic KPIs.
On-hold coordination test | IT | Meetings with Client / Partner | Proposal | Medium | On Hold | 2026-09-08 | 2026-09-15 | 25% | 6 | 1 |  | None |  | Automatically generated test task.
Quarterly reporting test | Strategic | Program Tracking & Monitoring | Report | High | Not Started | 2026-08-24 | 2026-10-23 | 15% | 20 | 2 |  | None |  | Automatically generated test task.
Status | Count
Not Started | 5
In Progress | 4
Completed | 1
On Hold | 1
Cancelled | 0
Overdue | 5

## Quarterly Report
Q3 2026 Task Report
01 Jul 2026 – 30 Sep 2026
Employee |  | Revision Ten Manager |  |  |  | Employee ID |  | R10-001 |  |  | Generated |  | 2026-09-13
Department |  | Academic Department |  |  |  | Job Title |  | Academy Manager |  |  | Report |  | Q3 2026
Total Tasks |  | Completed |  | In Progress |  | Overdue |  | Estimated Hours |  | Actual Hours |  | Completion Rate
17 |  | 2 |  | 6 |  | 10 |  | 129 |  | 50 |  | 11.76%
Task | Project | Task Category | Deliverable Type | Priority | Status | Start | Due | Progress | Estimated | Actual | Variance | Recurrence | Link | Notes
Complete curriculum outline, topic, competences, duration and draft pack | Academy Stage 2–8 Test Program | Program Tracking & Monitoring |  | High | Not Started | 2026-09-13 | 2026-09-13 | 80% | 2 | 0 |  | None |  | Workflow assignment · Curriculum
Review curriculum QA and lock release | Academy Stage 2–8 Test Program | Program Tracking & Monitoring |  | High | Not Started | 2026-09-13 | 2026-09-14 | 0% | 2 | 0 |  | None |  | Workflow assignment · Curriculum
Update student attendance report | Academic | Program Tracking & Monitoring | Report | Medium | Completed | 2026-08-02 | 2026-08-03 | 100% | 4 | 4 |  | Weekly |  | Validate late submissions.
Prepare weekly lesson plan | Academic | Curriculum Design | Course Outline | High | In Progress | 2026-08-02 | 2026-08-06 | 75% | 8 | 6 |  | Weekly |  | Coordinate subject plans.
Review IT support tickets | IT | Program Tracking & Monitoring | Report | High | Not Started | 2026-08-05 | 2026-08-06 | 20% | 6 | 1 |  | Daily |  | Prioritize classroom issues.
Facilities inspection | Operations | Review & Quality Check | Report | Medium | Not Started | 2026-08-06 | 2026-08-10 | 0% | 5 | 0 |  | Monthly |  | Inspect safety and maintenance.
Design social media campaign | Marketing | Slide & Material Production | Slide Deck | High | In Progress | 2026-08-04 | 2026-08-12 | 45% | 12 | 5 |  | Monthly |  | Back-to-school campaign.
Parent communication newsletter | Marketing | Meetings with Client / Partner | Proposal | Medium | On Hold | 2026-08-01 | 2026-08-20 | 30% | 10 | 3 |  | Monthly |  | Awaiting final announcements.
Completed test task | Administration | Administration | Report | Low | Completed | 2026-09-06 | 2026-09-07 | 100% | 2 | 2 |  | None |  | Automatically generated test task.
Overdue follow-up test | Operations | Meetings & Coordination | Report | High | In Progress | 2026-09-03 | 2026-09-07 | 65% | 4 | 3 |  | None |  | Automatically generated test task.
Today priority review | Academic | Review & Quality Check | Report | High | In Progress | 2026-09-08 | 2026-09-08 | 40% | 3 | 1 |  | None |  | Automatically generated test task.
Review readiness and record delivery decision | Academy Late-Stage Lifecycle Test | Program Tracking & Monitoring |  | High | Not Started | 2026-09-08 | 2026-09-08 | 0% | 2 | 0 |  | None |  | Workflow assignment · Readiness, Delivery & Assessment
Tomorrow content task | Marketing | Content Development | Web Page | Medium | Not Started | 2026-09-08 | 2026-09-09 | 0% | 5 | 0 |  | None |  | Automatically generated test task.
Weekly planning test | Academic | Program Tracking & Monitoring | Course Outline | Medium | In Progress | 2026-09-06 | 2026-09-10 | 55% | 8 | 4 |  | None |  | Automatically generated test task.
Quarterly academic performance review | Academic | Program Tracking & Monitoring | Report | High | In Progress | 2026-07-15 | 2026-09-15 | 60% | 30 | 18 |  | Quarterly |  | Review academic KPIs.
On-hold coordination test | IT | Meetings with Client / Partner | Proposal | Medium | On Hold | 2026-09-08 | 2026-09-15 | 25% | 6 | 1 |  | None |  | Automatically generated test task.
Quarterly reporting test | Strategic | Program Tracking & Monitoring | Report | High | Not Started | 2026-08-24 | 2026-10-23 | 15% | 20 | 2 |  | None |  | Automatically generated test task.
Status | Count
Not Started | 7
In Progress | 6
Completed | 2
On Hold | 2
Cancelled | 0
Overdue | 10